## Project Timeline
YOUR PROJECT
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2020-08-26 | Project Start | -5 | 1
2020-09-02 | Team Meetings set; Client Questions | 5 | 1
2020-09-09 | Project Plan set; Initial UI design | 10 | 1
2020-09-16 | Database draft; Code design draft | 15 | 1
2020-09-23 | 2nd contact with client - review designs | 20 | 1
2020-09-30 | UML diags final; proj plan final | 5 | 1
2020-10-07 | Database finalized | 10 | 1
2020-10-14 | Mid-semester peer reviews due | 15 | 1
2020-10-21 | IT system should be working | 5 | 1
2020-10-28 | Port code from VMs to IT env | 10 | 1
2020-11-04 | First Demo to client | -5 | 1
2020-11-11 | User Validation & Test plan finalized | 10 | 1
2020-11-18 | Deployment at client | -5 | 1
2020-11-25 | Documentation | 5 | 1
2020-11-25 | FINAL PRESENTATION! | 10 | 1
2020-12-09 | contingency | -5 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2020-08-26 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2020-08-26 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2020-08-26 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2020-09-02 | Team Meeting; 1st homework started | Have met at least once by the end of the day on 9/7; have started Homework #1 minimally - add more items to this project plan in the empty lines below and have altered this line to be something more meaninful than my babble… | All
9/3-9/4/2020 | Project Setup | Generate github repository. Ensure all members are listed as contributors. | All
9/5-9/8/2020 | Research | Meet with Professor Gormanly regarding CAS authentication. Scaffold Angular 10 project. Scaffold Asp.Net.Core WebApi. Research CAS authentication witth integration with Angular 10 and Asp.Net.Core WebApi 3.1 | All
2020-09-09 | Homework #1 Due! | Have met at least twice - this is your last reminder from me in this template that you need to meet regularly outside of class - if you are not, you will not do well in this class; Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | IS
9/10-9/15/2020 | ER CRUD | Basic CRUD operations accomplished through client application and backend. Establish ER diagram. | IS/CS
2020-09-16 | Homework #2 Due | Initial Design should be drafted… what do you envision the system looking like? Requirements full documented and ready for confirmation with the client. E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams. | All
9/17-9/22/2020 | CAS implementation | Authenticate authorize and establish user to database via CAS authentication | CS/IT
2020-09-23 | Homework #3 Due | Complete mock-ups (ie. wireframes) of your user interface. | CS
9/24-9/30/2020 | Implement UI design | Implement UI design | CS
2020-09-30 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams | IS
9/30-10/4/2020 | Research Email functionality | Research Email functionality | All
10/5-10/10/2020 | Implement Email Functionality | Implement Email Functionality | CS
10/11-10/14/2020 | Verify SPA web security | Research cookies JWTs, silent renew, cookies storing JWTs | CS
2020-10-14 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews | All
10/15-10/20/2020 | Get code production ready | Get code production ready | CS
10/21-10/25/2020 | Network configuration | Establish the best way to host our application | All
10/26-10/31/2020 | Deploy to docker container | Deploy to docker container | IT/CS
11/1-11/4/2020 | Start code documentaion | Start code documentaion | All
2020-11-04 | First Demo of Prototype | Complete project prototype first-pass demo ready | CS/IT
2020-11-11 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented | All
2020-11-18 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented | All
2020-11-18 | Draft Documentation | All documentation required for the project in Draft form | All
2020-11-25 | Paper Due - Final Documentation | All documentation required for the project in FINAL form | All
2020-11-25 | FINAL PRESENTATION! | Client will be on hand to accept / reject final project deliverables | All
2020-12-02 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All

## Weeks - Wednesday Section
Week | Class Topics and Activities | Assignments Due | Class Format
8/26 | Introduction; Project case study; Project plan; |  | Online, live webex, and
| Sections and Teams; Project overview |  | in classrooms 2nd floor
9/2 | Client Interview | Homework 1 due: requirements gathering questions & project plans/trello boards | Individual sections
(HC2023 available)
9/9 | IS = Project Mgt primer & team leadership | Homework 2 due: document | Group (HC2023 &
| CS = good design, code repository best practices | showing all requirements | other rooms for
|  | prioritized | breakouts: CS/IT/IS)
9/16 | Project Management and Design tooling | HW 3: rough draft of design / UML / use | Group (HC2023)
| (graphical tools to do mockups or models) | case diagrams / user stories | Algozzine on
project mgt
9/23 | Guest presentation: Alan Labouseur on | HW4: status report & finalized design & draft | Group (HC2023)
| database design and pitfalls | E/R Diagram (if appropriate) | Alan's talk
| Algozzine with IT & IS - review status / equipment |  | basement
9/30 | Status by team in class + work in class | HW5: status report & final E/R diagram | Individual Sections
10/7 | Status / work in class / help | Status report | Individual Sections
10/14 | Status / work in class / help | Status report | Individual Sections
10/21 | Status / work in class / help | Status report | Individual Sections
10/28 | CHECKPOINT: should be able to demo or | Status report | Individual Sections
even install something at client by now
11/4 | Presentation Practice & hints / tips | Status report | Individual Sections
11/11 | Client visit for final install | Status report | Individual Sections
11/18 | Final Presentations to client | Status report | Individual Sections
11/25 | Thanksgiving - NO CLASS
12/2 & 12/9 | Contigency / Hand in all code, documentation, deliverables | Final presentation & Client
documentation are due
Peer evaluations also due
All final docs due (last chance)

## Weekly Status Reports
Status Report - Team name, members
Date
RGY | Item | Description | Mitigation / Help needed
Red
Yellow
Green